INTERNAL OPERATING PLAYBOOK

# bits&bytes™ Originals
Techfest 2026

twelve city zonals and one national final at IIT Bombay

| 12 zonal hackathons | ₹2 crore gross sponsorship target | 80% high school participation target | 17 to 18 Dec IIT Bombay final |
| --- | --- | --- | --- |

One operating truth for everyone doing the work.

Version 1.0  |  10 September 2026  |  GOBITSNBYTES FOUNDATION

READ THIS FIRST

# The campaign is ambitious and the constraint is money

We are building twelve city hackathons that lead to a national final at IIT Bombay. The campaign is designed mainly for high school builders, with a campaign-wide target of at least 80 percent high school participation.

The uncomfortable version is simple: this campaign is expensive. If sponsorship stalls, the programme shrinks. The gross sponsorship target for the bits&bytes™ campaign is ₹2 crore. That number is aggressive, and this document does not pretend otherwise. It turns the target into one pipeline, one set of rules, and a weekly view of whether the work is moving.

This is the internal source of truth for the campaign. It explains what has been agreed, what we are currently planning, what remains open, and who is allowed to make which kind of commitment. It does not replace the signed partnership agreement or the Foundation's statutory and safeguarding obligations.

## What is fixed

Twelve city zonal hackathons will lead into one national final.

The national final is planned for 17 and 18 December 2026 at IIT Bombay.

The bits&bytes™ campaign has a gross sponsorship target of ₹2 crore.

At least 80 percent of verified participants across all twelve zonals should be high school students. This is not a per-city quota.

Zonals may use Mini, Original, or Extended formats.

## What is still open

Cities, city formats, exact zonal dates, capacities, qualification numbers, travel support, prizes, sponsor inventory, and detailed budgets remain open decisions. Blank space in this playbook is deliberate. It is safer than turning an early guess into team folklore.

## How to use this playbook

1.  Read the partnership, money, authority, and safeguarding sections before speaking for the campaign.

2.  Use the sponsor pipeline and city records during day-to-day execution.

3.  Use the weekly control room to see the campaign as a whole.

4.  Record material decisions and written approvals in the decision register.

DOCUMENT CONTROL

# How truth moves through this document

| Priority | Source | What it means |
| --- | --- | --- |
| 1 | Applicable law and statutory documents | Always controls |
| 2 | Executed Techfest partnership agreement | Controls the joint programme |
| 3 | Written joint decisions by authorised representatives | Updates operating decisions within the agreement |
| 4 | Board-approved Foundation policies | Controls internal authority, finance, brand, and safeguarding |
| 5 | This playbook | Current internal operating source of truth |
| 6 | Messages, call notes, and verbal instructions | Useful evidence, but they cannot silently change the playbook |

## Contents

1.  The partnership in plain English

2.  The programme model

3.  The campaign calendar

4.  The twelve city rollout

5.  Participants and qualification

6.  The sponsorship engine

7.  The outreach machine

8.  Commission rules

9.  Content and public communication

10.  Safeguarding and participant care

11.  Money authority and records

12.  Weekly control room

13.  Known risks and failure modes

14.  Decision register and working assumptions

## Status language

| Label | Meaning |
| --- | --- |
| Fixed | Confirmed by the agreement or an approved campaign decision |
| Working plan | The current direction, still subject to operational confirmation |
| Open decision | No answer has been approved yet |
| Needs written confirmation | The team has a working interpretation that must be confirmed before it is promised or applied |

PARTNERSHIP

# The partnership in plain English

Techfest IIT Bombay is the Lead Organiser and GOBITSNBYTES FOUNDATION is the Co Organiser for the 30th edition. The parties remain independent entities. The agreement creates a contractual collaboration for this event; it does not create a legal partnership, employment relationship, agency, or joint venture.

| Workstream | Techfest leads | bits&bytes™ leads |
| --- | --- | --- |
| Venue and infrastructure | IIT Bombay permissions, SAC venues, security, network, power, staging, and audiovisual logistics | Technical requirements for hackathon booths, power, and presentations |
| Outreach | College ambassador network and national festival channels | Teen and student builder mobilisation, communities, social campaigns, and registration drives |
| Sponsorship | Title sponsors, enterprise brands, institutional partners, and general festival funding | Developer tools, AI and cloud infrastructure, hardware, student kits, and track prize pools |
| Technical programme | Festival schedule integration and main stage coordination | Problem statements, tracks, workshops, judging rubrics, cohorts, and mentors |
| Zonal programme | Institutional coordination with regional host colleges | On-ground execution, workshops, qualification, and regional judging |
| Finalist experience | Campus hospitality, access, accommodation logistics, and ushering | Technical judges, mentors, submissions, evaluation, and live mentoring |

## What requires joint written approval

Material budget changes, venue changes, date changes, sponsor additions or removals with strategic significance, and substantial changes to the agreed plan.

Financial obligations above ₹25,000 unless the spend is already covered by a jointly approved budget line.

Co-branded public announcements and sponsor commitments that affect the other party's scope, cost, reputation, or legal obligations.

Operational work inside an approved lane can move without asking both parties about every small choice. When ownership is unclear, check Schedule 1 first, then the latest written joint decision.

## What contributors cannot do

Bind either organisation, sign contracts, or imply that a volunteer title creates legal authority.

Promise sponsor benefits, money, dates, venues, publicity, participant data, or exclusivity outside an approved package.

Collect or route funds through personal bank accounts, personal UPI IDs, wallets, or cash.

Publish a strategic announcement before the required approval is recorded.

PROGRAMME

# Three formats for twelve different city realities

The campaign has one identity and three possible zonal formats. A city does not earn status by running longer. The format should follow the venue, participant experience, budget, programme depth, and safeguarding readiness.

| Format | Duration | Use when | Minimum operating condition |
| --- | --- | --- | --- |
| bits&bytes™ Originals Mini | 8 to 12 hours | A city needs a compact build day or cannot safely support overnight participation | A complete challenge, judging flow, adult supervision, guardian and media consent, and a safe arrival and departure plan |
| bits&bytes™ Originals | 24 hours | The standard hackathon can run with safe overnight operations | All Mini controls plus overnight security, resting zones, chaperones, emergency coverage, and venue access control |
| bits&bytes™ Originals Extended | 36 to 48 hours | Extra build time materially improves the programme and the city can support it | All overnight controls plus stronger staffing rotations, food and rest planning, medical coverage, and a realistic budget |

## Format decision rule

A city may announce a format only after the venue, programme, finance, and safeguarding lanes confirm readiness in writing. If one lane is not ready, shorten the format or delay the announcement. The Extended format is optional, not a target.

## Campaign quality bar

Participants receive a clear problem, enough build time, accessible mentors, a transparent rubric, and a working submission path.

High school students are not treated as a marketing segment. The programme, supervision, language, schedule, and consent flow must be built for them.

Every sponsor benefit has an owner and can be delivered without weakening participant safety or privacy.

A city event is not confirmed until its venue and safeguarding plan are real.

CALENDAR

# The campaign calendar

| Window | Campaign phase | What must move |
| --- | --- | --- |
| 15 September | Registrations open | Registration, school outreach, city interest, guardian consent design, and public campaign launch |
| September to mid October | Cities become operational | Host conversations, venue checks, local teams, format choices, budgets, safety checks, and sponsor mapping |
| Mid October to 30 November | Twelve zonals run | City delivery, participant verification, judging, qualification, sponsor fulfilment, and post-event reporting |
| 1 to 16 December | Finalist runway | Eligibility verification, mentor support, travel and guardian documents, finalist communication, and showcase preparation |
| 17 and 18 December | IIT Bombay final | National final, judging, sponsor delivery, participant care, documentation, and closing records |
| By 31 December | Close and reconcile | Outstanding deliverables, financial reconciliation, settlements, data retention decisions, and the first impact report |

## The operating engine beneath the calendar

| Research | Approved outreach | Proposal and close | Cash received | Delivery and reporting |
| --- | --- | --- | --- | --- |
| Find accounts and the reason they may care | Assign one owner and use an approved message | Build only from approved inventory and terms | Count eligible cash only after it clears | Deliver the promise, record evidence, and close the loop |

Fundraising is not a phase that ends when registrations open. It runs through the entire campaign, alongside city delivery and content.

CITY ROLLOUT

# The twelve city rollout

No city is confirmed in version 1.0. The programme should choose cities for execution quality, not because a familiar name looks good on a map.

## City selection test

| Area | Question before selection |
| --- | --- |
| Audience | Can the city reach enough high school builders without compromising the campaign-wide 80 percent target? |
| Host | Is there a credible institution or venue partner with a named adult contact? |
| Venue | Is the venue available, accessible, safe, and appropriate for the proposed duration? |
| Local team | Is there enough execution capacity for outreach, operations, volunteers, judging, and reporting? |
| Safeguarding | Can the city meet consent, supervision, media, security, rest, and emergency requirements? |
| Budget | Can the event run within an approved budget without depending on speculative money? |
| Sponsor fit | Is there a credible local or national sponsor path without inventing benefits? |
| Calendar | Can the zonal finish by 30 November with enough time for finalist verification? |

## Campaign city register

| Slot | City | Format | Date | Readiness |
| --- | --- | --- | --- | --- |
| City 01 | Open | Open | Open | Open |
| City 02 | Open | Open | Open | Open |
| City 03 | Open | Open | Open | Open |
| City 04 | Open | Open | Open | Open |
| City 05 | Open | Open | Open | Open |
| City 06 | Open | Open | Open | Open |
| City 07 | Open | Open | Open | Open |
| City 08 | Open | Open | Open | Open |
| City 09 | Open | Open | Open | Open |
| City 10 | Open | Open | Open | Open |
| City 11 | Open | Open | Open | Open |
| City 12 | Open | Open | Open | Open |

CITY RECORDS

# City records 01 to 03

## City 01

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 02

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 03

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

CITY RECORDS

# City records 04 to 06

## City 04

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 05

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 06

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

CITY RECORDS

# City records 07 to 09

## City 07

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 08

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 09

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

CITY RECORDS

# City records 10 to 12

## City 10

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 11

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

## City 12

| City | ________________ | Status | Not selected |
| --- | --- | --- | --- |
| Host and venue | ________________ | Proposed date | ________________ |
| Format | Open decision | Capacity | Open decision |
| Local readiness | ________________ | Sponsor status | ________________ |

Safety gate  adult coverage ____  guardian workflow ____  perimeter and resting plan ____  emergency plan ____

Next decision  __________________________________________________________________________________

PARTICIPANTS

# The high school target belongs to the whole campaign

The 80 percent target is measured across verified participants in all twelve zonals. A city may sit above or below 80 percent. The combined campaign should finish at or above it.

## Measurement rule

Verified participant means a person whose eligibility and attendance have been confirmed under the campaign's registration process. Raw form submissions, duplicate registrations, cancelled registrations, and people who do not participate should not enter the denominator.

| Measure | Definition | Current value |
| --- | --- | --- |
| Verified participants | All verified participants across completed zonals | 0 |
| Verified high school participants | Verified participants attending school at the approved eligibility level | 0 |
| High school share | Verified high school participants divided by all verified participants | Not yet measurable |
| Target | Campaign-wide high school share | At least 80% |

## Qualification flow

1.  A zonal accepts submissions through the approved platform and deadline.

2.  Judges score eligible submissions against the approved rubric.

3.  The city team records results and resolves conflicts before announcing qualifiers.

4.  The programme verifies identity, eligibility, guardian documentation, and finalist availability.

5.  Only verified finalists enter the IIT Bombay final roster.

The number of qualifying teams per city, reserve-list rules, travel support, and finalist replacement rules are open decisions. They must be decided before the first zonal results are announced.

SPONSORSHIP

# The sponsorship engine

The campaign needs a lot of sponsors. That does not mean every company should receive the same pitch. The pipeline starts with a reason the sponsor fits, then moves through controlled outreach, an approved proposal, a signed agreement, payment, delivery, and reporting.

## What counts toward ₹2 crore

| Item | Counts toward target | Treatment |
| --- | --- | --- |
| Eligible sponsorship fee received | Yes | Count when cleared in the Foundation's official account |
| GST collected | No | Tax amount is not campaign sponsorship progress |
| Unpaid signed commitment | No | Track separately until cash clears |
| Refunded amount | No | Remove from eligible cash |
| Cloud credits or other in-kind support | No | Track at a separately documented value |
| Stall or eligible venue activation revenue | Separate | Apply the agreed revenue treatment only after the category is confirmed in writing |

## Sponsor categories to research

Developer tools, AI infrastructure, cloud platforms, data and cybersecurity products.

Hardware, electronics, robotics, maker tools, and prototyping support.

Education, learning, assessment, and student opportunity platforms.

Consumer brands that can support food, travel, participant kits, or safe on-ground activations.

Foundations and institutions that fund youth, STEM, access, or innovation programmes.

Sponsor package names, prices, exclusivity, speaking slots, data access, and event inventory remain open decisions. Nobody should improvise them in a call.

## Sponsor pipeline

| Stage | Meaning | Exit evidence |
| --- | --- | --- |
| Target account | Organisation identified with a plausible fit | Research note exists |
| Qualified | Need, category, budget path, and contact are credible | Reason to contact is recorded |
| Approved to contact | Ownership and message are cleared | One sponsor owner is assigned |
| Contacted | First outreach sent | Date, channel, and message recorded |
| Conversation | Sponsor has engaged | Need, timing, and next step recorded |
| Brief | A real opportunity is defined | Requested benefit and budget range are understood |
| Proposal approved | Offer, price, inventory, and approvals are ready | Authorised proposal is sent |
| Contracted | Agreement is executed by authorised signatories | Contract and deliverables are stored |
| Cash received | Eligible money has cleared | Finance record and commission basis are confirmed |
| Delivery | Sponsor benefits are being fulfilled | Evidence and owner are current |
| Closed | Delivery and reporting are complete | Renewal or closure note is recorded |

OUTREACH

# The outreach machine

The campaign needs 50 to 100 useful outreach contributors working through one shared pipeline, with clear lanes and one owner per sponsor account.

| Lane | Work | Handoff |
| --- | --- | --- |
| Research | Find organisations, decision makers, relevant programmes, and a credible reason to care | A qualified sponsor record with sources |
| Relationship outreach | Make introductions, send approved outreach, run discovery, and keep follow-ups alive | A recorded conversation and next step |
| Proposal support | Turn the sponsor need into approved inventory, pricing, and deliverables | An internally approved proposal |
| Finance and contracting | Approve money terms, issue documents, receive funds, and record commission basis | Executed documents and cleared-cash record |
| Sponsor delivery | Coordinate logos, sessions, stalls, credits, prizes, and evidence | Completed deliverable record |
| Content distribution | Keep the campaign visible and give outreach fresh proof to share | Published asset linked to the relevant city or sponsor story |

## Contributor onboarding

1.  Read this playbook and acknowledge the authority, privacy, brand, and money rules.

2.  Join one outreach lane and receive access only to the records needed for that work.

3.  Learn the current campaign brief, approved message, sponsor inventory, and escalation path.

4.  Claim work through the shared pipeline before contacting an account; record every material interaction and hand off when the work moves outside your authority.

## Daily and weekly rhythm

| Cadence | Action |
| --- | --- |
| Daily | Research, approved outreach, follow-ups, response logging, and urgent escalation |
| Twice weekly | Pipeline clean-up, proposal review, duplicate removal, and stalled-account decisions |
| Weekly | Campaign control room: cash, weighted pipeline, contributor activity, city readiness, content, risks, and approvals |
| Bi-weekly | Financial reconciliation with the joint-event records required by the agreement |

## Non-negotiable outreach rules

One sponsor account has one active owner. Contributors coordinate before contacting the same organisation.

No scraped personal contact list is shared beyond the approved working need.

Every claimed relationship, promise, meeting, and next step is recorded; never announce an uncontracted sponsor or invent metrics, city confirmations, or participant-data promises.

COMMISSION

# Commission rules

Anyone who gets the campaign a sponsor may earn commission. The commission recognises real sourcing work; it does not create signing authority, employment status, or ownership of the sponsor relationship.

| Rule | Operating treatment |
| --- | --- |
| Rate | Set case by case in writing between 1% and 3%. The absolute ceiling is 3%. |
| Approval | Record the approved rate and contributor before payout. Finance may require evidence of contribution. |
| Base | Eligible sponsorship cash received in the Foundation's official account, excluding GST, refunds, unpaid commitments, and in-kind support. |
| Timing | Commission becomes payable only after the eligible cash clears and finance verifies the basis. |
| Multiple contributors | The written approval must state how the total approved commission is divided. The combined payout cannot silently exceed the approved ceiling. |
| Minor contributor | Guardian documentation and finance approval are required before payout. The minor remains outside contracting, collection, and unapproved negotiation authority. |
| Dispute | Pause payout, preserve the evidence, and escalate through the finance and Board authority lane. |

## Illustrative calculation

If the Foundation receives an eligible sponsorship fee of ₹1,00,000 and the contributor's written rate is 1.5 percent, the commission basis is ₹1,00,000 and the commission is ₹1,500. GST collected on top of the fee, unpaid amounts, and in-kind credits do not increase that calculation.

This example explains the formula. It does not approve a rate or a payout for any real contributor.

## Commission approval record

| Field | Record |
| --- | --- |
| Contributor | ________________________________________ |
| Sponsor | ________________________________________ |
| Approved rate | ________ % between 1% and 3% |
| Contribution covered | ________________________________________ |
| Approval record | ________________________________________ |
| Eligible cash received | ₹ ______________________________________ |
| Verified commission | ₹ ______________________________________ |
| Payout status | ________________________________________ |

COMMUNICATION

# Content keeps outreach credible

Outreach needs proof that the campaign is alive. Content should give a sponsor or school something concrete to understand: who is building, what a city is preparing, what participants will do, and what has already happened.

| Moment | Useful content | Approval condition |
| --- | --- | --- |
| Campaign launch | Programme explanation, registration path, participation rules, and confirmed dates | Co-branding and strategic announcement approval |
| City preparation | Venue progress, local community stories, mentors, and challenge context | Publish only confirmed facts; obtain required consent |
| Zonal live coverage | Build progress, workshops, judging, and participant work | Media consent and safeguarding controls active |
| Zonal result | Projects, qualifiers, outcomes, and sponsor delivery | Results verified before publication |
| Finalist runway | Finalist projects, mentor support, and final preparation | Travel, identity, guardian, and media details cleared |
| IIT Bombay final | Final builds, judging, partner visibility, and outcomes | Joint event, brand, sponsor, and participant approvals |
| After the campaign | Impact report, delivery evidence, lessons, and renewal material | Confidential and participant data removed or authorised |

## Publishing rules

Use bits&bytes™ exactly in community-facing copy. Use GOBITSNBYTES FOUNDATION for legal, financial, and formal institutional contexts.

Use approved logo lockups and obtain approval for co-branded sponsor, school, press, or merchandise material.

Do not publish a city, date, venue, prize, speaker, sponsor, or finalist before it is confirmed through the relevant lane.

Do not share participant contact data with sponsors. Sponsor visibility may include approved branding, booths, and mentor access, subject to the agreement and safeguarding rules.

Store the final file, approval record, and publication link so sponsor delivery can be proved later.

SAFEGUARDING

# A youth campaign has to be built for youth safety

Most participants are expected to be high school students. Safety is therefore part of the event design, not a form added at the end. If a city cannot meet the required controls, it must shorten, move, or delay the event.

## Controls for every zonal

Verifiable parent or lawful guardian consent before processing a minor's personal data where required.

Separate written guardian release before photographing, recording, livestreaming, or publicly featuring a minor.

At least two vetted adults present for sessions involving minors; no isolated one-to-one physical or private online session.

A visible code of conduct, reporting channel, incident owner, and immediate escalation route.

Only necessary participant data is collected, access is limited, and sponsor access to personal contact data is prohibited.

Safe arrival, controlled access, emergency contacts, medical response, and documented departure procedures.

## Additional overnight gate

| Requirement | Evidence before announcement |
| --- | --- |
| Venue perimeter and access control | Written venue plan and responsible adult contact |
| Gender-separated resting areas | Mapped spaces with supervision and access rules |
| Chaperones and adult rotations | Named vetted adults, shifts, and escalation contacts |
| Guardian consent | Approved consent workflow covering the overnight format, travel, media, and emergency contact |
| Food, water, rest, and medical support | Operating plan and vendors or venue support confirmed |
| Arrival and departure | Safe timing, pickup or travel instructions, and exception handling |
| Incident response | Reporting path, immediate protection steps, partner notification, and statutory escalation where required |

## Stop conditions

Pause registration, promotion, or the event itself when a material safeguarding control is missing, a serious incident is unresolved, venue security fails, or a partner cannot meet the agreed minor-protection standard. The partnership agreement allows the Foundation to suspend promotional support, withhold participation, or terminate for compromised safety standards.

MONEY AND AUTHORITY

# Money moves through official accounts and recorded approvals

| Control | Rule |
| --- | --- |
| Fund routing | Use approved Foundation corporate accounts or official Techfest institutional accounts as permitted by the agreement. Never use personal accounts, personal UPI IDs, wallets, or cash. |
| Joint spend threshold | An Event obligation above ₹25,000 needs prior written consent from the other party unless it sits within a pre-approved joint budget line. |
| Local Fork sponsorship | A city Fork may raise local event sponsorship up to ₹50,000. A deal above that requires HQ CFO approval. |
| Foundation high-value authority | Contracts, disbursements, or legal obligations above ₹1,00,000 require the Foundation's dual-signature control under the current authority rule. |
| Sponsorship agreements | Only authorised corporate officers or Board signatories may execute sponsorship contracts and MOUs. |
| Reconciliation | Maintain transparent records, reconcile bi-weekly during execution, and complete final settlement within the agreement's timeline. |

## The 60 to 40 interpretation

The current internal intention is that eligible commercial activations using Techfest-provided venue inventory, such as stalls, are split 60 percent to GOBITSNBYTES FOUNDATION and 40 percent to Techfest. For example, ₹100 of eligible activation revenue would allocate ₹60 to the Foundation and ₹40 to Techfest, subject to taxes and the agreed calculation basis.

Do not treat that narrow interpretation as settled yet. Clause 7.4 and Addendum A of the executed agreement describe the 60 to 40 category more broadly as zonal sponsorship and on-ground advertising revenue. Obtain written confirmation from Techfest before quoting, allocating, or contracting on the narrower basis.

## Intellectual property and confidentiality

Each party keeps its pre-existing brands, tools, templates, content, and other background intellectual property.

Event-specific material created collaboratively is shared Event IP under Addendum B and cannot be commercially transferred without both parties' written consent.

Both parties may use approved Event IP for promotion, portfolio, impact reporting, and education with proper attribution.

Sponsor terms, participant data, financial records, internal processes, and non-public plans remain confidential. The agreement's confidentiality obligations survive for two years.

CONTROL ROOM

# Weekly campaign dashboard

This page is the weekly truth. Update it before the campaign review, use one reporting cut-off, and link to evidence instead of debating numbers from memory.

| Measure | Target or definition | Current | Status |
| --- | --- | --- | --- |
| City slots selected | 12 | 0 | Open |
| Cities safety-ready | All announced cities | 0 | Open |
| Verified participants | Campaign total | 0 | Not started |
| High school share | At least 80% campaign-wide | Not measurable | Not started |
| Active outreach contributors | 50 to 100 | 0 | Building |
| Qualified sponsor pipeline | Weekly approved pipeline value | ₹ 0 | Building |
| Contracted sponsorship | Executed eligible sponsorship value | ₹ 0 | Not started |
| Eligible cash received | ₹2 crore gross target | ₹ 0 | Not started |
| Sponsor deliverables overdue | 0 | 0 | On track |
| Open safeguarding issues | 0 unresolved material issues | 0 | On track |
| Decisions overdue | 0 | 0 | On track |

## Weekly review order

1.  Safety and incidents first.

2.  Money received, invoices, refunds, and reconciliation.

3.  Sponsor pipeline by next action, not by optimistic headline value.

4.  City readiness and decisions blocking announcements or delivery.

5.  Participant mix and the campaign-wide high school percentage.

6.  Sponsor deliverables, content shipped, and approvals due.

## The question at the end of every review

What is the smallest set of decisions and actions that materially improves safety, cash received, or city readiness before the next review?

RISK

# Known failure modes

| Risk | Early signal | Response |
| --- | --- | --- |
| Sponsorship shortfall | Pipeline value, conversations, proposals, or cash received lag the required pace | Narrow sponsor segments, improve proof, increase qualified ownership, protect core programme scope, and stop budgeting against unsigned money |
| Duplicate outreach | A sponsor receives multiple uncoordinated messages | Enforce one account owner and merge duplicate records immediately |
| Unapproved promises | A proposal contains benefits, dates, or inventory that are not confirmed | Pause the proposal, correct the record, and obtain the required approval |
| Weak city operator | Venue, adults, reporting, or local follow-through remains vague | Add support, reduce format, replace the city, or delay confirmation |
| Late venue confirmation | A city approaches promotion without written venue readiness | Do not announce; move or shorten the event |
| Unsafe overnight plan | Rest, supervision, consent, access, or emergency coverage is incomplete | Use Mini, change the venue, delay, or cancel |
| Participant imbalance | The combined high school share trends below 80% | Shift school outreach and later-city capacity while keeping city access flexible |
| Sponsor delivery debt | Brand assets, sessions, stalls, or reports lack owners and evidence | Freeze new promises in that lane until delivery is recovered |
| Approval delay | Joint or Board decisions sit without a deadline or escalation | Record the decision, deadline, impact, and escalation path |
| Privacy breach | Participant data is copied, shared, or requested outside the approved need | Restrict access, preserve evidence, notify the authorised incident lane, and follow legal reporting duties |

## Programme fallback order

1.  Remove speculative benefits and spending.

2.  Shorten a city from Extended to Original or Mini when the longer format is the risk.

3.  Reduce city capacity before weakening safety, judging, or participant support.

4.  Move or replace a city that cannot clear its venue and safeguarding gates.

5.  Protect the national final and the strongest zonal experiences rather than pretending every early ambition is still funded.

DECISIONS

# Decision register and working assumptions

| Decision | Operating lane | Needed by | Status | Closing record |
| --- | --- | --- | --- | --- |
| Confirm the scope of the 60 to 40 revenue category with Techfest | Board, finance, partnership | Before related sponsor proposals | Needs written confirmation | Written joint confirmation or amendment |
| Select twelve cities | Programme and partnerships | Before each city announcement | Open | Approved city register |
| Choose format for each city | Programme, venue, safeguarding, finance | Before each city announcement | Open | City readiness record |
| Set exact zonal dates | Programme and host institutions | Before registration allocation | Open | Approved campaign calendar |
| Set capacity for each city | Programme, venue, safeguarding | Before registration allocation | Open | City capacity record |
| Set qualification numbers and reserve rules | Programme and judging | Before first zonal results | Open | Qualification policy |
| Set finalist travel and guardian model | Programme, finance, safeguarding | Before first zonal results | Open | Finalist operations plan |
| Approve sponsor inventory, prices, and exclusivity rules | Partnership, programme, finance, brand | Before proposals | Open | Approved sponsorship prospectus |
| Approve city and final budgets | Programme and finance | Before commitments | Open | Approved budget and authority record |
| Set outreach activity targets | Outreach operations | Before contributor launch | Open | Weekly outreach operating brief |

## Change log

| Version | Date | Change | Approved record |
| --- | --- | --- | --- |
| 1.0 | 10 September 2026 | Initial internal operating playbook | Founding campaign brief and executed partnership agreement |

## Primary source references

Partnership Agreement for Co Organisation between Techfest IIT Bombay and GOBITSNBYTES FOUNDATION, executed September 2026, including Schedule 1 and Addenda A and B.

GOBITSNBYTES FOUNDATION e-Memorandum of Association and e-Articles of Association.

Foundation policies on parental consent, dual adult supervision, overnight hackathon safety, media consent, sponsor execution, cash prohibition, sponsor data privacy, local sponsorship authority, and dual-signature controls.

bits&bytes™ design system and brand usage rules.